## Backlog
Subject | I want to... | Theme | Priority | Status | Notes
Primitives | Engine specific and platform independent primitive types | Core | Required | TODO
Logging | Log useful data from the engine sub systems | Core | Required | TODO
Profiling |  | Core | Future | Research
Random numbers | Generate random integer and decimal numbers | Core | Required | TODO
Assertions | Static and runtime assertions. Runtime assertions are able to log data. | Core | Required | TODO
Unit testing | Test each module properly | Core | Required | TODO
Networking |  | Core | Future | Research
Localization |  | Core | Future | Research
Memory allocation and management | Basic allocators | Core | Required | TODO
Parsers | Parse XML and Json | Core | Required | TODO
Serialization/RTTI/Reflection |  | Core | Required | Research
Configuration | Load and save configuration files, for systems like input and renderer | Core | Required | TODO
Strings | Type definition of C++ string and utility class | Core | Required | TODO
File I/O | FileSystem wich allows easy access to files and directories | Core | Required | TODO
Math | Basic math, vector and matrice implementations | Core | Required | TODO
Threading |  | Core | Future | Research
Graphics wrapper | Platform independent graphics wrapper that hides implementation details | Core | Required | TODO
Environment |  | Core | Future | Research

## Sprint #1
From | To
2015-06-23 | 2015-06-30
Legend
Task | Author | Desc | Status | In progress
Filesystem | siquel |  |  | Done
File | siquel |  |  | Problems
Directory | siquel
Wrappers | siquel
Reading & Writing | siquel
Bytes | siquel
Graphics
GraphicsDevice | Voidbab & siquel | Sum up after sprint
DirectX 11 | Voidbab | Study how D3D works; Testing and stuff;
OpenGL 3 | Voidbab | Should be pretty straightforward;
OpenGLES 2 | Voidbab | Same as with D3D
Parsers | Voidbab
XML | Voidbab
Wrappers | Voidbab
Logging | Not assigned
Console logger
File logger
Logging features
Math | siquel
Vectors | siquel | Vector 2, 3 and 4 | Done
Matrices | siquel | Matrix 2, 3 and 4
Quaternions | siquel | Rotations
Rectangles | siquel | AABB's and basic functions
Functions | siquel | Helpers, randoms
Configuration | Not assigned
Create var lists
Load files
Primitives | Both
Typedefs
Timers | Not assigned
Stopwatch
Callback timer
Time